## 55 Tradescant
Address | Item | Cost | cost inc 4.5% uplift | % complete | Total Valued
55 TRADESCANT ROAD | Remove existing floor covering to hall floor, prepare floor and lay Polysafe vinyl | 252.89 | 252.89 | 100% | 252.89
55 TRADESCANT ROAD | Scaffolding | 5303 | 5541.635 | 100% | 5541.635
55 TRADESCANT ROAD | Front Entrance Door Install | 1367.8 | 1367.8 | 100% | 1367.8
55 TRADESCANT ROAD | Replace bricks (individual), remove existing mortar and defective brick, replace with brick to match existing, repoint in gauged mortar to match existing, 5% of wall area. (Item Added in) | 80.465 | 80.465 | 100% | 80.465
55 TRADESCANT ROAD | Rake out joints to existing brickwork; repoint in gauged mortar to match existing, 25% of wall area. (Item Added in) | 126.445 | 126.445 | 100% | 126.445
55 TRADESCANT ROAD | Prepare masonry features to 2nr window surrounds and apply two coats masonry paint to match existing | 20.691 | 20.691 | 100% | 20.691
55 TRADESCANT ROAD | Prepare masonry features to bay window surrounds and apply two coats masonry paint to match existing | 31.0365 | 31.0365 | 100% | 31.0365
55 TRADESCANT ROAD | Prepare masonry lintels to 2 nr windows and apply two coats masonry paint to match existing | 10.6381 | 10.6381 | 100% | 10.6381
55 TRADESCANT ROAD | Prepare masonry features to door surrounds and apply two coats masonry paint to match existing | 20.691 | 20.691 | 100% | 20.691
55 TRADESCANT ROAD | VS : Re-render window cills 0.5m2 - Hack off loose, hollow or defective render, prepare substrate, apply two coat cement lime sand render finish to match existing | 25.289 | 25.289 | 100% | 25.289
55 TRADESCANT ROAD | Please allow to hack off defective mansonry to right hand side of front entrance doorway. Renew and form to suit profle ready to receive new decoration. (0.25M2) | 62.7 | 62.7 | 100% | 62.7
55 TRADESCANT ROAD | Please allow to hack off defective render front bay window cill. Renew and form to suit profle ready to receive new decoration. (0.25M2) | 62.7 | 62.7 | 100% | 62.7
55 TRADESCANT ROAD | 1 nr bay window to ground floor | 28.4658 | 28.4658 | 100% | 28.4658
55 TRADESCANT ROAD | 3 nr windows to first floor | 256.1922 | 256.1922 | 100% | 256.1922
55 TRADESCANT ROAD | 3 nr windows to second floor | 256.1922 | 256.1922 | 100% | 256.1922
55 TRADESCANT ROAD | 2 nr windows to ground floor VS : + 1 Casement | 113.8632 | 113.8632 | 100% | 113.8632
55 TRADESCANT ROAD | 4 nr windows to first floor | 455.4528 | 455.4528 | 100% | 455.4528
55 TRADESCANT ROAD | 4 nr window to second floor | 455.4528 | 455.4528 | 100% | 455.4528
55 TRADESCANT ROAD | Prepare glazed timber door and frame to rear door, cut out defective timber and replace, apply two coats gloss paint, externally | 22.4361 | 22.4361 | 100% | 22.4361
55 TRADESCANT ROAD | Prepare glazed timber door, fanlight and frame to front door, cut out defective timber and replace, apply two coats gloss paint, externally | 26.1877 | 26.1877 | 100% | 26.1877
55 TRADESCANT ROAD | Prepare metal railings and apply two coats gloss paint to match existing | 42.3225 | 42.3225 | 100% | 42.3225
55 TRADESCANT ROAD | Prepare metal gate and apply two coats gloss paint to match existing | 9.3527 | 9.3527 | 100% | 9.3527
55 TRADESCANT ROAD | Please allow to cut out defective pointing to a depth of 25mm and repoint in gauged mortar to suit. (0.25M2) | 35.4046 | 35.4046 | 100% | 35.4046
55 TRADESCANT ROAD | Prepare timber door, fanlight and frame to front door, cut out defective timber and replace, apply two coats gloss paint, internally | 26.1877 | 26.1877 | 100% | 26.1877
55 TRADESCANT ROAD | Wash down hall walls, prepare and paint one mist coat and two full coats of emulsion paint; prepare existing woodwork and apply two undercoats and one gloss coat. | 309.32 | 309.32 | 100% | 309.32
55 TRADESCANT ROAD | Prepare hall ceiling and paint one mist coat and two full coats of emulsion paint. | 51.414 | 51.414 | 100% | 51.414
55 TRADESCANT ROAD | Attend to visit flat 2 to replace glazing, ease and adjust, overhaul and decorate windows which have been painted and nailed shut internally. | 580 | 580 | 50% | 290
55 TRADESCANT ROAD | Survey and replace glazing to bay window of flat 1, renew all putties and decorate. | 160 | 160 | 100% | 160
55 TRADESCANT ROAD | Beams to rear - unforseen at tender | 200 | 200 | 100% | 200
55 TRADESCANT ROAD | Erect suspended scaffold above rear roof elevation | 540 | 540 | 100% | 540
55 TRADESCANT ROAD | Access through property due to rear unable to go up and over | 600 | 600 | 100% | 600
55 TRADESCANT ROAD | Building Control Application | 222 | 222 | 100% | 222
11703.225